## OPPM template
Project 2, 244-586-AB, Analog Clock w/ alarm | [6 empty] | Maya A. Rosales O.
Linking Tasks to Objectives |  |  |  |  | ID | Task Description | Status | January |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | Lead or Support
|  | 8 |  |  | T1 | Research (Initial) | D | ● | ●
|  | 8 |  | 8 | T2 | Coding (Clock) | D |  | ● | ● | ● | ● | ● |  |  |  | ● | ● | ●
| 8 |  |  | 8 | T3 | Analog Gear (Clock gearbox) | D | [9 empty] | ● | ● |  | ● | ●
8 | 8 |  | 8 |  | T4 | 3D model | D |  |  |  | ● | [5 empty] | ● |  |  | ● | ●
|  | 8 |  |  | T5 | Coding (Music Player) | D | [10 empty] | ● | ●
|  |  | 8 |  | T6 | Print Board | D | [9 empty] | ● |  |  | ● | ●
|  | 8 | 8 |  | T7 | Wiring | D | [9 empty] | ● |  |  |  | ●
8 | 8 | 8 |  |  | T8 | Case | D | [12 empty] | ● | ●
8 |  |  |  |  | T9 | Engraving & Staining | D | [13 empty] | ● | ●
8 |  | 8 | 8 | 8 | T10 | Final Assembly | D | [13 empty] | ● | ●
|  |  | 8 | 8 | T11 | Troubleshooting | D | [6 empty] | ● | ● | [7 empty] | ●
|  |  | 8 |  | T12 | Continuous Updating | D | [10 empty] | ● | ● |  |  |  | ● | ●
|  |  | 8 | 8 | T13 | Continuous Research | D | ●
Linking KPIs to Objectives | [5 empty] | Risks, Quantitatives, Other Metrics | Status
8 | 8 |  |  |  | KPIs | Noise
|  | 8 |  | 8 |  | Reliability
8 | 8 | 8 | 8 |  |  | Aesthetics
8 | 8 |  |  |  |  | Size
8 |  |  | 8 | 8 |  | Cost
KEY OBJECTIVES
Aesthetically Pleasant Clock | Keep Clock's size relatively Small | Intuitive Usage | Keeping Low cost | Precision (resolution) & Reliability |  |  |  | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[9 empty] | UNPLANNED | O |  | CHECKING | C |  | MILESTONE | ◊
[9 empty] | PLANNING | P |  | DONE | A |  | PLANNED | ○
[9 empty] | DOING | D |  | Link symbol: | 8 |  | COMPLETED | ●
Objectives
Major Tasks
Objectives
NOTES:
Legend
Target Dates